## Slide 1
Keukengerij Launch
0 → €10k+/maand · 90 dagen · EU10 · Dropship
Ali · Kheibar · Farshad
v1.0 · 2026-09-09
Strategic Roadmap + Execution Plan

## Slide 2
Executive Summary
Wat
Keukengerij e-commerce launch in EU10. 10 producten, gefaseerde wave-based introductie. Shopify als enige kanaal. Dropship-only fulfilment.
Waarom
HK-only seller structuur (bewust gekozen) voor tax-efficiency. Eigen merk opbouwen voor lange-termijn exit-potentieel. AI-first aanpak via Hermes.
Hoe
Team van 3 founders (33% elk). €5-10k budget + €1000 eerste weken ad spend. 30% ACoS target. 6 fasen, 90 dagen.
Targets (eerste 90 dagen)
Doel
Maximaliseren (geen vast target-getal)
ACoS
30% (break-even ROAS 3.33)
Retour
14 dgn, wij betalen retourlabel
Ad budget eerste weken
€1000 (~€35/dag)
Customer service
24h response, 7 talen, AI-chatbot
Brand positioning
Mid-range met mix budget/premium
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 3
Team · 33% per persoon
Ali
Strategie · Marketing · Content · AI-agents
Ownership: 33%
Stigma, marketing, content generation, Hermes orchestration
Kheibar
Finance · Banking · Payouts
Ownership: 33%
HK bank, WISE, Currency Ways, payment infrastructure
Farshad
E-com operator · Supplier netwerk
Ownership: 33%
Dropship supplier in China, quality check, designer (zijn team)
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 4
Product Strategy · 10 keukengerij SKU's
Wave-based launch · 3-4 producten per wave · 14-dgn test cyclus
Wave 1 · D20-D35
3-4 SKUs
Eerste validatie, kill losers
Wave 2 · D40-D55
3-4 nieuwe SKUs
Anders segment dan W1
Wave 3 · D51-D65
3-4 final SKUs
Portfolio compleet
Pricing strategie · Mid-range met mix budget/premium
Budget
€15-25
Gadgets, tools, messensets <€30
Mid
€30-50
Pannen, snijplanken, keukensets
Premium
€50-80
High-end messen, speciale pannen
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 5
Channels · EU10 · Multi-language
Hoofdkanaal (90 dagen)
Shopify webshop
Multi-currency · Multi-language · Dropship-only
UITGESLOTEN in 90 dagen
TikTok Shop
Marktplaats
Amazon EU
bol.com
Etsy
EU10 markten (Amazon EU set)
NL
BE
DE
FR
IT
ES
PL
SE
IE
CZ
Talen: NL · EN · DE · FR · IT · ES · PL (+ meer via AI vertaling)
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 6
⚠️ Compliance Disclosure · HK-only seller
Jullie hebben expliciet gekozen voor een HK-bedrijf als enige seller.
Dit brengt bekende risico's met zich mee. Mitigatie in de roadmap.
GPSR Responsible Person
Extern service (~€50-150/SKU/jaar)
Douane / Btw
Klanten kunnen btw-verrassingen krijgen bij import (geen IOSS)
NL-belastingdienst
DAC7 reporting via Shopify/Meta/WISE — wereldwijd inkomen belastbaar omdat Ali fiscaal inwoner NL is
Productaansprakelijkheid
Blijft gelden ongeacht seller-land
AVB verzekering
Aanbevolen voor keuken-producten (food contact)
Aanbeveling: NL-belastingadviseur voor DAC7 compliance monitoring (jaarlijks, niet in 90-dgn roadmap)

## Slide 7
F0
Foundations
D-7 → D0 · doel: HK live, Shopify opgezet, design klaar, alle infra
HK bank account aanmaken
Kheibar
vrijdag
WISE + Currency Ways accounts
Kheibar
vrijdag
HK bedrijf oprichten
Kheibar
vrijdag
Shopify master + Markets setup
Farshad
D-7
Custom theme design
Designer
D-5 → D-1
GPSR Responsible Person service
Ali
D-5
Privacy + Cookie + Terms + Returns policies
Hermes
D-3
Shopify Inbox + chatbot widget
Ali
D-2
GA4 + Meta Pixel
Hermes
D-2
Introductie Farshad's China supplier
Farshad
ma
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 8
F1
Brand + Product Setup
D0 → D14 · doel: Brand naam, logo, 10 producten, listings in voorbereiding
Brand voice document (Ali)
Ali
D0
Brand naam brainstorm (60 namen)
Ali
D0-D1
EUIPO + WIPO trademark search
Ali
D1
Brand naam lock-in
Ali
D2
Logo design
Designer
D2-D5
Product onderzoek (10 producten)
Ali
vrijdag
Pain/Diff/Ad-ability score × 10
Ali
D2
Amazon scrape (per segment)
Hermes
D2
Supplier shortlist per SKU
Farshad
D3-D5
Sample aanvragen × 10 SKUs
Farshad
D5
Sample quality check
Farshad
D10-D14
Per-product compliance check
Ali
D7
GPSR × 10 SKUs
Ali
D10
Product page copy × 10
Ali
D10-D14
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 9
F2
Listings + Wave 1 Launch
D14 → D35 · doel: 10 listings live, Wave 1 eerste ads
Product photos × 10 SKUs (5-8/product)
Designer
D14-D18
Product videos × 10 SKUs
Designer
D15-D20
Listings live × 10
Farshad
D18
Pricing per SKU
Ali
D18
FAQ × 10 SKUs
Hermes
D19
Wave 1 selectie (3-4 SKUs)
Ali
D20
UGC + AI Higgsfield × 10/SKU
Ali
D20-D24
Meta Ads Wave 1 launch
Ali
D25
Google Ads Wave 1 launch
Ali
D27
Email flows live
Ali
D24
Daily metrics dashboard
Hermes
D26
Wave 1 review (D+14)
Ali
D39
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 10
F3
Wave 2 + Wave 3 + Validation
D35 → D65 · doel: Alle 3 waves getest, winners geïdentificeerd
Wave 2 selectie + listings + video's
Ali/Farshad
D40-D44
Wave 2 ads launch
Ali
D45
Wave 2 review (D+14)
Ali
D59
Wave 3 selectie + listings + video's
Ali/Farshad
D51-D55
Wave 3 ads launch
Ali
D56
Wave 3 review (D+14)
Ali
D70
Kill rules automation script
Hermes
D36
Per-SKU dashboard
Hermes
D38
Cohort analysis tooling
Hermes
D50
Customer survey NPS
Ali
D55
Weekly review meetings
Ali
D36+
Decision log per SKU
Ali
D36+
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 11
F4
Scale Winners
D65 → D85 · doel: Budget omhoog op winners, repeat halo start
Winners definitief (3 SKUs)
Ali
D65
Scale budget €100/dag/winner
Ali
D67
Lookalikes op kopers
Ali
D68
Creative refresh elke 14 dgn
Ali
D70+
Google PMax campaigns
Ali
D72
Email flow post-purchase upsell
Ali
D75
Email flow win-back (60d)
Ali
D78
Bundle pricing tests
Ali
D75
Cross-SKU recommendations
Hermes
D80
LTV:CAC dashboard per channel
Hermes
D78
Repeat-buyer cohort analyse
Hermes
D82
Cash forecast 4-weken runway
Kheibar
D85
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 12
F5
Lock + Optimize
D85 → D90 · doel: Optimalisaties, documentatie, exit-potentieel assessment
Eindstand metrics review
Ali
D87
Lessons learned doc
Ali
D88
Updated roadmap v2.0
Hermes
D89
Supplier scorecard
Farshad
D88
Customer feedback analysis
Ali
D89
Compliance audit
Ali
D89
Financial close-out (90 dgn P&L)
Kheibar
D90
Exit-potentieel assessment
Ali
D90
NL-belastingadvies call
Ali
D90+
Influencer strategy (post-90)
Ali
D90+
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 13
Recurring Operations · Dagelijks ritme
Dagelijks 30 min
Morning metrics (Hermes cron)
Sys
Telegram digest 06:30
09:00
Customer service sweep
Ali/Kheibar/Farshad
Shopify Inbox
12:00
Trend-spotting + content scroll
Ali
TikTok/IG
18:00
Content post (1 video/brand)
Ali
Multi-language
21:00
EOD notes deposit
Ali
Hermes eod
22:00
Review queue (5/brand)
Ali
Shopify
Wekelijks
Ma 08:00
Auto-sourcing bottom-5 vervangen
Sys
Di 14:00
Weekly review (Ali + Kheibar + Farshad)
Ali
Wo 10:00
Ad-budget + bid adjustments
Ali
Wo 16:00
Supplier check-in
Farshad
Vr 14:00
Bulk order decisions
Farshad
Vr 16:00
Cash forecast update
Kheibar
Zo 21:00
Weekly Telegram digest (auto)
Sys
F0: Foundations
F1: Brand+Products
F2: Listings+Wave 1
F3: Wave 2+3+Validation
F4: Scale Winners
F5: Lock+Optimize

## Slide 14
Next Steps · Eerste 14 dagen
vrijdag 12 sept
HK entity + bank + WISE + Currency Ways
Kheibar
vrijdag 12 sept
Product research (10 producten)
Ali
vrijdag 12 sept
Brand naam input delen met Hermes
Ali
ma 15 sept
Introductie Farshad's China supplier
Farshad
D-7 (zondag)
Shopify master + Markets setup start
Farshad
D-5
GPSR Responsible Person service kiezen
Ali
D-5
Trademark search (vóór naam lock-in)
Ali
D-2
Compliance disclosure met Kheibar + Farshad reviewen
Allen
D0
GO/NO-GO 🚀
Allen
📱 Companion webapp: Vercel-deployed voor live tracking per owner + status
Filters per Ali/Kheibar/Farshad/Designer/Hermes · Status checkboxes · Comments per taak